## Stakeholder Register
Stakeholder ID | Stakeholder | Role | Department/Area | Responsibilities | Interest | Influence | Engagement Level | Key Needs / Expectations | Communication Method | Frequency
STK-001 | Customer | Primary user | Retail Banking | Register, submit application, upload documents and track application | High | High | Manage Closely | Simple application process, status visibility, notifications | Digital notifications / surveys | As required
STK-002 | Customer Service Agent | Operational user | Customer Service | Assist customers and respond to onboarding queries | High | Medium | Keep Informed | Easy access to application status and customer information | Email / team meetings | Weekly
STK-003 | KYC Analyst | Process owner | Compliance / KYC | Verify customer identity and supporting documents | High | High | Manage Closely | Complete and accurate customer information, verification workflow | Workshops / email / system reports | Weekly
STK-004 | Branch Manager | Business stakeholder | Branch Operations | Monitor onboarding activity and operational performance | High | High | Manage Closely | Application visibility, exception handling and KPIs | Management meetings / dashboard | Weekly
STK-005 | Compliance Officer | Control stakeholder | Compliance | Define and monitor compliance requirements | High | High | Manage Closely | Auditability, required data and compliance controls | Requirements workshops / reports | At milestones
STK-006 | Operations Manager | Business stakeholder | Operations | Monitor onboarding process and operational efficiency | High | High | Manage Closely | Processing-time metrics, queues and operational reporting | Dashboard / management meetings | Weekly
STK-007 | IT Team | Technical stakeholder | Information Technology | Design, develop, integrate and support the solution | Medium | High | Keep Satisfied | Clear requirements, interfaces, security and technical constraints | Technical workshops / project meetings | Weekly
STK-008 | Executive Management | Project sponsor | Executive Management | Provide strategic direction and approve major decisions | High | High | Manage Closely | Business value, risks, costs, progress and KPIs | Steering meetings / executive dashboard | Monthly
STK-009 | System Administrator | System support | Information Technology | Manage user access, roles and system administration | Medium | Medium | Keep Informed | Role-based access, audit logs and administration controls | Email / support meetings | As required

## Power Interest Matrix
Quadrant | Stakeholders | Engagement Approach
Manage Closely | Customer; KYC Analyst; Branch Manager; Compliance Officer; Operations Manager; Executive Management | Frequent engagement, workshops, decision reviews and progress reporting.
Keep Satisfied | IT Team | Provide clear requirements, involve in technical decisions and monitor dependencies.
Keep Informed | Customer Service Agent; System Administrator | Provide regular updates, training information and relevant documentation.
Monitor | None identified at this stage | Monitor for changes in influence or interest.

## RACI Matrix
Activity | Customer | Customer Service | KYC Analyst | Branch Manager | Compliance | Operations | IT Team | Executive Mgmt | System Admin
Define business problem | C | C | C | A | C | R | C | A | I
Gather requirements | C | R | R | A | C | R | C | I | I
Analyse AS-IS process | C | R | R | A | C | R | C | I | I
Define business rules | I | C | R | C | A | C | C | I | I
Define functional requirements | I | C | R | C | C | A | R | I | C
Approve requirements | I | C | C | A | A | C | C | R | I
Design solution | I | C | C | C | C | C | R/A | I | C
User acceptance testing | R | R | R | A | C | C | R | I | C
Go-live approval | I | C | C | A | C | R | R | A | C

## Communication Plan
Stakeholder Group | Information Needed | Communication Purpose | Channel | Owner | Frequency
Executive Management | Project status, risks, milestones, KPIs | Decision-making and oversight | Steering meeting / dashboard | Business Analyst | Monthly
Branch Manager / Operations | Application volumes, bottlenecks, process issues | Operational management | Meeting / dashboard | Business Analyst | Weekly
KYC / Compliance | Requirements, exceptions, verification issues | Control and compliance alignment | Workshop / email | Business Analyst | Weekly / milestones
Customer Service | Process changes, FAQs, training | Operational readiness | Team meeting / documentation | Business Analyst | Bi-weekly
IT Team | Functional requirements, data, integrations, priorities | Solution delivery alignment | Technical workshop / backlog | Business Analyst | Weekly
Customers | Application progress and required actions | Customer awareness and completion | Portal / email / SMS | System | As required